## Status Overview
Slice | Name | Goal (What You Test) | Status | Started | Completed
1 | Two Guys on a Flat Board | Move, attack, enemy responds, someone wins on a flat grid | ⬜ Not started
2 | Terrain and Height | Elevation, terrain costs, high ground bonus, blocking objects | ⬜ Not started
3 | Skills and Real Combat | Skills with MP/range/AOE, status effects tick, AI uses skills | ⬜ Not started
4 | Loadouts and Saving | Equip items, get loot, save/load game progress | ⬜ Not started
5 | Procedural Maps | Random map generated each battle, always playable | ⬜ Not started
6 | Full Content Expansion | All skills, biomes, races, doctrines, weapons loaded | ⬜ Not started

## Slice 1 - Flat Board
Goal: | Press Play. See a small flat grid. Two units. Move one, attack the other. Enemy takes its turn. Someone dies. Battle ends.
Done When: | You can play a full fight (move, attack, enemy responds, someone wins) without errors. Numbers match Game Rules formulas.
Task | Status | Notes
Flat grid renders in Roblox Studio (8×8 or 10×10 for testing) | ⬜
Two units placed on the grid (one player, one enemy) | ⬜
CT/RT timeline runs — correct unit becomes ready first | ⬜
Player can select their unit and see movement range highlighted | ⬜
Player clicks a tile → unit moves there (cardinal + diagonal, cost 1) | ⬜
Movement costs AP (1 AP) and adds RT correctly | ⬜
Player can select Basic Attack → valid target highlighted → confirm → damage dealt | ⬜
Damage uses correct formula: Weapon Damage × (1 + STR / 200) − Defense | ⬜
HP updates visibly on the target unit | ⬜
Turn ends → RT assigned → clock advances → next ready unit gets turn | ⬜
Enemy AI: walks toward player, attacks if in range (Tier 1+2 only) | ⬜
KO works: unit at 0 HP is removed/marked dead | ⬜
Win condition: all enemies dead → Battle Won message | ⬜
Lose condition: all player units dead → Battle Lost message | ⬜

## Slice 2 - Terrain Height
Goal: | Same battle, but board has hills, mud, walls. Height matters. Mud slows you. High ground gives damage bonus.
Done When: | Battle on uneven terrain plays correctly. Units path around walls, slow on mud, benefit from high ground. AI navigates properly.
Task | Status | Notes
Grid tiles have elevation values (0, 1, 2, 3) | ⬜
Visual difference between elevation levels | ⬜
Jump stat works: unit can only climb ≤ Jump per step | ⬜
Downward Jump works: can drop Jump + 2 voluntarily | ⬜
At least 3 terrain types rendered (Clear, Grassland, Mud) | ⬜
Terrain cost applies: Mud = 2, Clear/Grassland = 1 | ⬜
Movement range accounts for terrain cost correctly | ⬜
Blocking objects placed (rocks/walls can't be walked through) | ⬜
Elevation damage bonus works: higher attacker deals more | ⬜
Elevation defense bonus works: lower attacker deals less | ⬜
Fall damage works: forced off a height → takes damage | ⬜
AI navigates around obstacles and considers terrain cost | ⬜

## Slice 3 - Skills Combat
Goal: | Units have 2-3 skills. Pick a skill, select target area, confirm. Status effects tick. Combat feels like a real tactics game.
Done When: | 3v3 battle with skills and statuses feels like a real tactical RPG. Poison ticks, AOE hits, healing works, AI makes reasonable choices.
Task | Status | Notes
Skill Card UI: player sees available skills with MP cost and range | ⬜
Selecting a skill shows valid target tiles/units highlighted | ⬜
At least one single-target damage skill works (e.g., Power Strike) | ⬜
At least one AOE skill works (e.g., Line or Cleave pattern) | ⬜
At least one support/healing skill works | ⬜
MP cost deducted on use; can't use if MP too low | ⬜
Skill RT cost applied correctly (different from Basic Attack RT) | ⬜
Skill Power formula calculates correctly (weapon + stat scaling) | ⬜
At least 2 status effects: Poison (DoT) and Burn (DoT + spread) | ⬜
Status duration ticks down correctly | ⬜
Status damage applies at correct timing | ⬜
Status visual indicator on affected units | ⬜
Channel Time works: skill with channel shows delay before activating | ⬜
Trigger safety: on-hit effects fire once per target, no loops | ⬜
Enemy AI uses skills (not just Basic Attack) | ⬜
Enemy AI picks appropriate skill (heal if low HP, attack otherwise) | ⬜

## Slice 4 - Loadouts Saving
Goal: | Win battle → get loot. Go to menu, equip it. Save. Close Roblox, reopen — everything still there.
Done When: | Play multiple battles, collect loot, equip gear, save, close, reopen — progress intact. Different weapons change combat.
Task | Status | Notes
Battle end → reward screen shows loot (1-2 items) | ⬜
Item generation works: rarity, random stat bonuses, BP validation | ⬜
Items appear in inventory | ⬜
Menu UI: player can view roster of units | ⬜
Menu UI: player can view inventory of items | ⬜
Player can equip a weapon → unit stats change | ⬜
Equipment affects combat: different weapon = different damage/WT/range | ⬜
Weapon WT applies to Basic Attack RT correctly | ⬜
Save writes to Roblox DataStore (compact numeric format) | ⬜
Load reads from DataStore and rebuilds full state | ⬜
Save survives closing and reopening the game | ⬜
Save split: roster in key 1, inventory in key 2 | ⬜
Lookup table approach: save stores IDs, game resolves to full data | ⬜
Doctrine equip works: stat package applies | ⬜
At least 3 weapon types feel different (Sword, Spear, Bow) | ⬜

## Slice 5 - Procedural Maps
Goal: | Game generates a random map before battle. Different every time. Always playable. One biome + one template.
Done When: | Every battle has a different but valid map. No broken maps, no freeze, no unreachable enemies.
Task | Status | Notes
Map generation runs on the server (not client) | ⬜
Seed-based: same seed → same map (deterministic) | ⬜
Plains biome profile loads terrain weights correctly | ⬜
T01 Frontline Pressure template places PD, ED, LAN zones | ⬜
Terrain fills grid based on biome weights | ⬜
Regions form (connected groups of similar terrain) | ⬜
Elevation assigned consistent with biome profile | ⬜
Connectivity validation: player can reach enemies via LAN | ⬜
Objects placed without blocking required paths | ⬜
If generation fails → retry (up to 3 attempts) | ⬜
Generation completes within 2 seconds | ⬜
Frame yielding: no visible freeze during generation | ⬜
Generated map renders correctly in Roblox Studio | ⬜
Pre-generation: map ready before player enters battle | ⬜
All Slice 1-4 systems work on the generated map | ⬜

## Slice 6 - Content Expansion
Goal: | Fill with all designed content. Systems work — this is volume and variety.
Done When: | 20+ battles without repeating. Biomes feel distinct. Different builds create different playstyles.
Task | Status | Notes
All 15 Races implemented with passives and growth rates | ⬜
All 15 Doctrines implemented with stat packages and skills | ⬜
Full Skill catalog loaded (all entries from Game Rules) | ⬜
Full Augment catalog loaded (all Active entries) | ⬜
All conventional weapon archetypes (15 types) | ⬜
All status effects (damage, control, buff/state) | ⬜
All 8 templates (T01-T08) for map generation | ⬜
All biomes (Plains through Beach — 12 total) | ⬜
All terrain types with transformations working | ⬜
All map objects with interactions | ⬜
Encounter generation: different enemies per biome | ⬜
Battle conditions active (Rain, Thunderstorm, Heatwave, etc.) | ⬜
Loot tables tuned per source (Normal, Elite, Boss) | ⬜
Fortune system fully functional | ⬜
Guild progression system | ⬜
Multiple quest types available | ⬜
Balance pass: nothing feels obviously broken | ⬜

## How To Use
Topic | Instructions
Marking progress | Change ⬜ to ✅ in the Status column when a task is working in Roblox Studio
Updating overview | When all items in a slice are ✅, update Status Overview and fill in the Completed date
Starting new session | Tell AI: "Read my game docs in D:\AI\Projects\CTRBLXAI\docs. Check the roadmap for where I am."
One slice = multiple sessions | Each slice may take many chat sessions. That's normal.
Order matters | Don't skip ahead. Later slices depend on earlier ones working.
Notes column | Track issues, decisions, or things to revisit.