## Status Overview
Slice | Name | Goal (What You Test) | Status | Started | Completed
1 | Two Guys on a Flat Board | Move, attack, enemy responds, someone wins on a flat grid | ✅ Done | 2026-08-20 | 2026-08-20
2 | Terrain and Height | Elevation, terrain costs, high ground bonus, blocking objects | ✅ Done | 2026-08-21 | 2026-08-21
3 | Skills and Real Combat | Skills with MP/range/AOE, status effects tick, AI uses skills | ✅ Done | 2026-08-23 | 2026-08-23
4 | Loadouts and Saving | Equip items, get loot, save/load game progress | ✅ Done | 2026-08-24 | 2026-08-31
5 | Procedural Maps | Random map generated each battle, always playable | 🔄 In Progress — near complete (map-gen rework source-verified 2026-09-30; Studio tests pending)
6 | Full Content Expansion | All skills, biomes, races, doctrines, weapons loaded | ⬜ Not started
7 | Visual Polish | Visual/audio pass: terrain, animations, VFX, UI, camera, sound | 🔄 In Progress — Stage 1 Complete, Stage 2 (Battle UI + Loadout) In Progress | 2026-08-29
Slice 8 — Guild Base and Out-of-Battle Systems | ⬜ Not Started | Guild Base hub, merchants, recruitment, quests, dispatch, explore, services, acquisitions
7 | Visuals & UI | Battle animations, mobile UI, CT timeline bar, polish | ⬜ Not started
8 | Base Building & Multiplayer | HQ facilities, base progression, multiplayer/co-op, live service | ⬜ Not started
9 | Dungeons | STS-style branching paths, exclusive loot, avatar mutation events | ⬜ Not started

## Slice Development Model
SLICE DEVELOPMENT MODEL
A slice is a broad player-facing development milestone handled in a dedicated AI conversation where practical.
Each slice owns a defined group of modules. When completed: behavior verified, public APIs recorded, internals protected, Git checkpoint recorded.
Later slices consume APIs instead of rewriting internals. Completed slices are not permanently immutable — backward-compatible additions may be approved.
FOUR MODULE CLASSIFICATIONS
Classification | Definition | Rules
Slice-Owned | Modules primarily owned by one slice | Owning slice modifies normally. After completion, later slices consume through public APIs.
Protected Completed | Modules belonging to a completed slice | Later slices: read, require, consume events. Must not rewrite internals for convenience, style, cleanup, or refactoring.
Shared Integration | Modules where multiple systems meet | Every modification requires: exact purpose, smallest diff, no unrelated cleanup, explicit approval, regression test, Git checkpoint.
Content/Config Authority | CTRBLXAI.db, skill/weapon/status definitions, templates | Rule ownership in Game Rules. Presentation slices must not change gameplay values to make a screen easier.
CROSS-SLICE COMPATIBILITY PROCESS
Step | Action
1 | Identify exact missing API, event, callback, or data field
2 | Identify owning slice and module
3 | Determine if existing API or visual fallback works
4 | Do NOT duplicate formula, validation, state, or data
5 | If no fallback, produce a compatibility request
6 | Obtain explicit developer approval before editing protected/shared module
7 | Apply smallest backward-compatible interface addition
8 | Do not change existing authoritative behavior
9 | Run owning slice's minimum regression test
10 | Commit compatibility change before continuing requesting slice
11 | Record as compatibility addition — ownership does NOT transfer
DEPENDENCY DIRECTION (preferred)
Authoritative rules/content → gameplay services → shared events/payloads → functional client controllers → presentation adapters/views
Forbidden: combat services requiring UI, map gen requiring visual layout, save services reading UI state, gameplay formulas depending on presentation assets
MINIMUM CROSS-SLICE SMOKE TEST
After every verified phase touching UI, shared client, or battle presentation:
1. Battle starts
2. Expected units appear
3. First player turn begins
4. Movement reaches confirmation/execution path
5. Basic Attack reaches targeting and execution
6. One Skill targets and resolves
7. Next action or turn begins
8. UI input does not trigger battlefield actions behind panels
9. No new causal runtime error in Output
RISK-BASED WORKFLOW | Scope | Process
Low Risk | Theme, colors, typography, spacing, panel positions, assets, VFX, audio | Inspect → implement → sanity check → visual UAT → smoke test → commit
Medium Risk | Shared client events, presentation adapters, responsive reflow, camera integration | Impact check → smallest change → focused audit → focused UAT → smoke test → commit
High Risk | Combat formulas, target legality, CT/RT, save data, inventory, map gen, server payloads | Compatibility request → approval → focused impl → owning-slice regression → integration test → commit

## Prior Work
Prior Prototype Code — Available for Reuse in Slice 5
File | Location | What It Does | Reusable For | Slice
T01_FrontlinePressure.lua | ReplicatedStorage/CTRBLXAI/Templates/ | Defines T01 template grid (30×20) with PD, ED, LAN, HZD, BLK, POI, ADV, NEU zones using fillRect | Template data for map generation | Slice 5
TileDefinitions.lua | ReplicatedStorage/CTRBLXAI/Shared/ | Color definitions for all 9 template markers (PD, ED, LAN, POI, ADV, HZD, BLK, WAT, NEU) | Visual rendering of template zones | Slice 5
RegionGenerator.lua | ServerScriptService/ | Generates random connected regions using seed-based growth. Guarantees: every tile gets one region, regions are cardinally connected, minimum size enforced. | Core region generation logic for procedural maps | Slice 5
GridGenerator.lua | ServerScriptService/ | Simple 3-region hardcoded grid (City/Beach/Sea) with corridor. Early prototype — likely replaced by RegionGenerator. | Mostly obsolete. Corridor concept may inform LAN paths. | Replaced
MapGenerator.lua | ServerScriptService/ | Creates Roblox Part instances for a 20×30 grid with color-coded regions. Visualization only. | Tile rendering pattern (Part creation, positioning, attributes) | Slice 5
TemplateViewer.server.lua | ServerScriptService/ | Combines RegionGenerator + T01 template + TileDefinitions. Renders full 30×20 map with template overlay and region ownership. Grid overlay. Debug attributes on every tile. | Primary visual prototype — demonstrates template+region integration | Slice 5
TemplateInspector.client.lua | StarterPlayer/StarterPlayerScripts/ | Client-side hover/click inspector with tile info panel, view mode toggle (Region/Template), adaptive grid lines, selection boxes. | Debug/inspector tool for map development | Slice 5
Main.server.lua | ServerScriptService/ | Entry point — currently just calls MapGenerator.Generate(). 3 lines. | Will need complete rewrite for game architecture | N/A
Summary
What was built: | A visual template + region viewer prototype. You can see a color-coded map in Roblox Studio with zone markers and random regions.
What was NOT built: | No combat, no units, no movement, no attacks, no AI, no skills, no items, no saving. No actual gameplay.
Roadmap impact: | This code is early Slice 5 work (procedural map rendering). Slices 1–4 have not been started. Nothing to cross off yet.
Reuse plan: | When you reach Slice 5, RegionGenerator, TemplateViewer, T01 template data, and TileDefinitions can be reused or adapted.

## Slice 1 - Flat Board
Goal: | Press Play. See a small flat grid. Two units. Move one, attack the other. Enemy takes its turn. Someone dies. Battle ends.
Done When: | You can play a full fight (move, attack, enemy responds, someone wins) without errors. Numbers match Game Rules formulas.
Task | Status | Notes
Flat grid renders in Roblox Studio (8×8 or 10×10 for testing) | ✅
Two units placed on the grid (one player, one enemy) | ✅
CT/RT timeline runs — correct unit becomes ready first | ✅
Player can select their unit and see movement range highlighted | ✅
Player clicks a tile → unit moves there (cardinal + diagonal, cost 1) | ✅
Movement costs AP (1 AP) and adds RT correctly | ✅
Player can select Basic Attack → valid target highlighted → confirm → damage dealt | ✅
Damage uses correct formula: Weapon Damage × (1 + STR / 200) − Defense | ✅
HP updates visibly on the target unit | ✅
Turn ends → RT assigned → clock advances → next ready unit gets turn | ✅
Enemy AI: walks toward player, attacks if in range (Tier 1+2 only) | ✅
KO works: unit at 0 HP is removed/marked dead | ✅
Win condition: all enemies dead → Battle Won message | ✅
Lose condition: all player units dead → Battle Lost message | ✅
═══ SLICE OWNERSHIP ═══
Functional Scope | Core battle lifecycle, CT/RT progression, ready units/turns, AP turns, basic Move + Basic Attack flow, basic AI, KO, victory/defeat
Owned Module Group | BattleCoordinator.lua, UnitSchema.lua, GameConstants.lua
Shared Integration Modules | Main.server.lua, BattleEvents.lua
Protected Dependencies | None (first slice)
Public Contracts Provided | Battle lifecycle events, unit turn results, CT/RT advancement, KO/victory/defeat signals
Public Contracts Consumed | None
Forbidden Changes | Later slices must not change CT, RT, KO, victory, defeat, or turn progression without a compatibility request
Minimum Regression Gate | Battle starts, units take turns, Basic Attack resolves, KO triggers, victory fires once
Checkpoint Commit | Completed 2026-08-20

## Slice 2 - Terrain Height
Goal: | Same battle, but board has hills, mud, walls. Height matters. Mud slows you. High ground gives damage bonus.
Done When: | Battle on uneven terrain plays correctly. Units path around walls, slow on mud, benefit from high ground. AI navigates properly.
Task | Status | Notes
Grid tiles have elevation values (0, 1, 2, 3) | ✅
Visual difference between elevation levels | ✅
Jump stat works: unit can only climb ≤ Jump per step | ✅
Downward Jump works: can drop Jump + 2 voluntarily | ✅
At least 3 terrain types rendered (Clear, Grassland, Mud) | ✅
Terrain cost applies: Mud = 2, Clear/Grassland = 1 | ✅
Movement range accounts for terrain cost correctly | ✅
Blocking objects placed (rocks/walls can't be walked through) | ✅
Elevation damage bonus works: higher attacker deals more | ✅
Elevation defense bonus works: lower attacker deals less | ✅
Fall damage works: forced off a height → takes damage | ⏭️ | Deferred — no forced displacement system yet
AI navigates around obstacles and considers terrain cost | ✅
═══ SLICE OWNERSHIP ═══
Functional Scope | Terrain movement, elevation, Jump, pathing, blocking, target geometry, range, battlefield legality, displacement/push physics (collision, fall damage)
Owned Module Group | TargetingService.lua, TileDefinitions.lua, DisplacementService.lua
Shared Integration Modules | Main.server.lua, GameConstants.lua
Protected Dependencies | Slice 1 (battle lifecycle, turn system)
Public Contracts Provided | Movement candidates, target candidates, range validation, elevation data, Jump/pathing APIs, displacement resolution (push/knockback, collision, fall damage)
Public Contracts Consumed | Slice 1 battle lifecycle, unit state
Forbidden Changes | Later slices may display movement/target candidates but must not recalculate them
Minimum Regression Gate | Movement respects terrain cost, elevation blocks correctly, Jump works, range validates
Checkpoint Commit | Completed 2026-08-21

## Slice 3 - Skills Combat
Goal: | Units have 2-3 skills. Pick a skill, select target area, confirm. Status effects tick. Combat feels like a real tactics game.
Done When: | 3v3 battle with skills and statuses feels like a real tactical RPG. Poison ticks, AOE hits, healing works, AI makes reasonable choices.
Task | Status | Notes
Player input system: client sends commands to server, server validates via CommandService | ✅ | PREREQUISITE — without this, all other Slice 3 items are untestable by the player
Battle runs 3v3 (3 player units, 3 enemy units) to test timeline with multiple units | ✅ | PREREQUISITE — proves targeting, turn order, and AI with multiple units per side
Skill Card UI: player sees available skills with MP cost and range | ✅ | Verified in source code audit 2026-08-23
Selecting a skill shows valid target tiles/units highlighted | ✅ | Verified in source code audit 2026-08-23
At least one single-target damage skill works (e.g., Power Strike) | ✅ | Already working from Slice 2 implementation
At least one AOE skill works (e.g., Line or Cleave pattern) | ✅ | Verified in source code audit 2026-08-23
At least one support/healing skill works | ✅ | Verified in source code audit 2026-08-23
MP cost deducted on use; can't use if MP too low | ✅ | Verified in source code audit 2026-08-23
Skill RT cost applied correctly (different from Basic Attack RT) | ✅ | Already working from Slice 2 implementation
Skill Power formula calculates correctly (weapon + stat scaling) | ✅ | Already working from Slice 2 implementation
At least 2 status effects: Poison (DoT) and Burn (DoT + spread) | ✅ | Verified in source code audit 2026-08-23
Status duration ticks down correctly | ✅ | Already working from Slice 2 implementation
Status damage applies at correct timing | ✅ | Verified in source code audit 2026-08-23
Status visual indicator on affected units | ✅ | Already working from Slice 2 implementation
Channel Time works: skill with channel shows delay before activating | ✅ | Verified in source code audit 2026-08-23
Trigger safety: on-hit effects fire once per target, no loops | ✅ | Already working from Slice 2 implementation
Enemy AI uses skills (not just Basic Attack) | ✅ | Already working from Slice 2 implementation
Enemy AI picks appropriate skill (heal if low HP, attack otherwise) | ✅ | Verified in source code audit 2026-08-23
═══ SLICE OWNERSHIP ═══
Functional Scope | Client command submission, server validation, Skills, AOE/patterns, MP/costs, statuses, channeling, combat resolution, trigger safety, skill AI, Guard, Push command
Owned Module Group | CommandService.lua, CombatResolver.lua, StatusService.lua
Shared Integration Modules | Main.server.lua, BattleEvents.lua, BattleVisualBroadcaster.lua, GameConstants.lua
Protected Dependencies | Slice 1 (battle lifecycle), Slice 2 (targeting, range)
Public Contracts Provided | Command validation, damage/healing outcomes, status events, skill resolution, Guard mitigation, Push command validation and execution
Public Contracts Consumed | Slice 1 turn system, Slice 2 targeting/range
Forbidden Changes | Slice 7 may present these but must not own transitions, validation, or calculations
Minimum Regression Gate | Skill spends MP, channeling completes/interrupts, Poison/Burn tick, AOE resolves, Guard mitigates, AI uses skills
Checkpoint Commit | Completed 2026-08-23
═══ SLICE 3 FOUNDATION EXPANSION (post-completion) ═══
--- Phase 1: Status Definitions ---
GameConstants.STATUSES expanded from 4 → 36 entries (all DB statuses) | ✅ | Includes Sleep, Silence, Stun, Petrify, Haste, Wet, Frozen, etc.
--- Phase 2: StatusService Expansion ---
StatusService.IsActionBlocked exists (Silence→skills, Disarmed→attack, Pinned→move) | 🔄 | Sleep/Stun/Petrify blocking implemented; Disarmed/Pinned referenced but not fully tested
Turn-skipping statuses (Sleep, Petrify, Stun) in BattleCoordinator | ⬜ | Needs verification
Hard CC removes Guard on application | ⬜ | Sleep/Petrify should remove Guard — needs verification
Status tick behaviors beyond DoT (Haste RT mod, Regeneration, Weakened, etc.) | ⬜ | 36 statuses defined; most tick behaviors not yet in StatusService runtime
Reapplication rules per status | ⬜ | DB defines per-status reapplication; StatusService may not enforce all
--- Phase 3: Element System ---
Element tag extraction in CombatResolver | 🔄 | Element extraction logic exists; full interaction chain incomplete
Element→status triggers (Fire→Burn, Water→Wet, Ice+Wet→Frozen) | ⬜
Element weakness/resistance multipliers | ⬜ | Depends on Phase 5 race tags for full effect
Healing element interactions (Holy vs Undead) | ⬜ | Depends on Phase 5 Undead tag
--- Phase 4: Status Immunity Framework ---
Immunity check before status application | ⬜ | No IsImmune check in StatusService.ApplyStatus
Race-tag immunities registered (Undead, Mechanical) | ⬜
Debuff Resistance stat functional (VIT-based) | ⬜ | Still defaults to 1.0 in code
--- Phase 5: Race Tag Functional Effects ---
Race tags stored on unit at creation | ⬜ | RaceData has tags; UnitSchema doesn't copy to unit.tags
Undead: healing reversal, Holy×2, immunities | ⬜
Mechanical: WT+15%, immunities, Wet doubled | ⬜
Amphibious: water movement, Drowning immunity | ⬜ | Blocked — no water tiles in combat
Flying: permanent Flight | ⬜ | Blocked — Flight status not fully implemented
Giant: melee elevation range, knockback | ⬜ | Giant tag added to DB (2026-09-04)
--- Phase 6: Race Passive Evaluation ---
RacePassiveService.lua created with 8 query functions | ✅ | 6.4KB — integrated into CombatResolver, CommandService, TargetingService, EquipmentService
Orc Bloodlust (below 50% HP → +15% damage) | ✅ | In RacePassiveService.GetDamageDealtModifier
Dwarf Stout Resilience (physical DR -10%, Move -1) | ✅ | DR in GetDamageReceivedModifier, Move in GetMovementRangeModifier
Fairy Fae Grace (AOE DR -25%, STR -15%) | ✅ | DR in GetDamageReceivedModifier, STR in GetStatModifiers
Golem Fortified Frame (Guard +20%, Move -1) | ✅ | Guard in GetGuardMitigationBonus, Move in GetMovementRangeModifier
Zombie Undying (Move -1) | 🔄 | Movement penalty applied; revive NOT implemented (no revive system)
Elf Elven Focus (MP Cost -20%) | ✅ | In RacePassiveService.GetMpCostModifier
Elf Jump +1 | ❌ | NOT applied — ComputeDerivedStats uses formula only, no race bonus
Goblin Basic Attack applies Poison | 🔄 | GetBasicAttackStatus returns 'Poison'; needs CombatResolver integration verification
Elemental Spirit elemental damage +30%/-30% | ✅ | In GetDamageDealtModifier and GetDamageReceivedModifier
Lich Arcane Corruption (Light damage received +50%) | ✅ | In GetDamageReceivedModifier
Shadow Umbral Veil (elemental DR +10%; Hide pending) | 🔄 | DR applied; Hide-on-hit NOT implemented (no Hide status)
Titan CanEquip2HAsWith1H | ✅ | In RacePassiveService and EquipmentService
Vampire lifesteal (15%/5%) | ❌ | NOT implemented
Human Adaptability (EXP +10%, +1 stat/3 levels) | ❌ | Blocked — no leveling/EXP system
Android Push→Pull | ❌ | Blocked — DisplacementService needs Pull mechanic
Catau Tidecaller (water tile bonuses) | ❌ | Blocked — no water tiles in combat
--- Phase 7: Content Registry Bridge ---
SkillData.lua generated (89 skills from DB) | ✅ | 118KB data file
AugmentData.lua generated (102 augments from DB) | ✅ | 91KB data file
DoctrineData.lua generated (32 doctrines from DB) | ✅ | 33KB data file
Registry.lua facade (GetSkill/GetAugment/GetDoctrine) | ✅
Battle systems consume Content Registry instead of hardcoded GameConstants.SKILLS | ❌ | CommandService/CombatResolver still use 6 hardcoded skills
Formula evaluator for SkillData string formulas | ❌

## Slice 4 - Loadouts Saving
Goal: | Win battle → get loot. Equip gear. Save. Close, reopen — progress persists. Slice 4 owns functional behavior and data contracts. Final visual polish belongs to Slice 7.
Done When: | Functional lifecycle verified: battle → reward → persist → roster/inventory/equip → save → reload → confirm.
Task | Status | Notes
Item generation works: rarity, random stat bonuses, BP validation | ✅
Items committed to inventory after qualifying victory | ✅
Player can equip a weapon → unit stats change | ✅
Equipment affects combat: different weapon = different damage/WT/range | ✅
Weapon WT applies to Basic Attack RT correctly | ✅
Save writes to Roblox DataStore (compact numeric format) | ✅
Load reads from DataStore and rebuilds full state | ✅
Save survives closing and reopening the game | ✅
Save split: roster in key 1, inventory in key 2 | ✅
Lookup table approach: save stores IDs, game resolves to full data | ✅
Doctrine equip works: stat package applies | ✅
At least 3 weapon types feel different (Sword, Spear, Bow) | ✅
--- Persistent HP/MP (bundled into Slice 4) ---
UnitSchema accepts persistent HP/MP instead of defaulting to full | ✅ | Pass currentHp/currentMp from save state
MP Regen system: accumulator + CT-based tick | ✅ | GameConstants + BattleCoordinator
Battle-end: persist final HP/MP + apply 35% recovery | ✅ | Main.server.lua hook
Battle-start: load persistent HP/MP from save state | ✅ | Main.server.lua
KO units get zero recovery, flagged in save | ✅
═══ SLICE 4D — REWARDS, MANAGEMENT CONTRACTS, AND LOADOUT TRANSACTIONS ═══
Goal: | Winning a qualifying battle awards persistent loot exactly once. Player can retrieve authoritative roster, inventory, equipment, and deployment data and submit server-validated equip/unequip requests. Slice 4D establishes functional data and interaction contracts. Final layout, theme, cards, icons, animations, responsive presentation, and visual polish belong to Slice 7.
--- 4D.1 — Battle Reward Transaction ---
Qualifying-victory detection | ✅ | Slice 4 owned
Reward-opportunity creation + reward count | ✅
Rarity selection from authoritative runtime data | ✅ | Single runtime authority for loot rarity weights
Item Level source: per-enemy = enemy level | ✅ | Encounter-completion Item Level: UNRESOLVED — BLOCKER
Item generation via ItemGenerator | ✅
Inventory commitment before save export | ✅ | NON-ATOMIC: one item per call, no batch, no rollback
Duplicate-processing protection | ✅ | Local boolean prototype only — not durable across rejoin
Save ordering: commit rewards → export → save | ✅
Reward summary payload to client | ✅
Failure reporting | ✅
--- 4D.2 — Reward Presentation Contract ---
Reward-summary payload (ownership committed before display) | ✅ | Slice 4 owned
Continue intent + Skip intent | ✅ | Slice 4 owned
Functional completion state + destination after Continue | ✅ | Slice 4 owned
PRESENTATION DEPENDENCY: Victory banner, reward cards, rarity glow, reveal animation, Continue/Skip buttons, timing, responsive layout, UI sound, VFX | ⏭️ Slice 7 | Slice 7 owned — do not build inside Slice 4
--- 4D.3 — Roster Data Contract ---
Owned unit list with full persistent state (HP/MP/KO/equipment/doctrine/skills/augments/deployment) | ✅ | Slice 4 owned
Functional unit-selection intent | ✅
PRESENTATION DEPENDENCY: Unit-card layout, HP/MP bars, KO icon, portraits, responsive roster layout | ⏭️ Slice 7 | Slice 7 owned
--- 4D.4 — Inventory Data Contract ---
Complete item instances (identity, level, rarity, stats, bonuses, passives, equipped state) | ✅ | Slice 4 owned
Functional filter/sort values + item-selection intent | ✅
PRESENTATION DEPENDENCY: Item-grid, item-card, icons, rarity borders, detail layout, filter/sort controls | ⏭️ Slice 7 | Slice 7 owned
--- 4D.5 — Equip/Unequip Transaction ---
Server-validated equip/unequip (ownership, slot, handedness, legality) | ✅ | Slice 4 owned
Off-hand clearing, duplicate prevention, loadout legality | ✅
Stat rebuild after successful mutation | ✅ | Exactly once
Before-and-after authoritative values for comparison | ✅ | Slice 4 supplies; Slice 7 presents
Persistence after successful mutation | ✅
PRESENTATION DEPENDENCY: Slot layout, comparison display, stat-delta colors, confirm/back, error tooltips | ⏭️ Slice 7 | Slice 7 owned
--- 4D.6 — Deployment Resource Data Contract ---
Persistent HP/MP/KO, deployment eligibility, functional warning/unavailable reason | ✅ | Slice 4 owned
Deployment selection intent | ✅
PRESENTATION DEPENDENCY: Resource bars, colors, warning presentation, KO symbol, responsive layout | ⏭️ Slice 7 | Slice 7 owned — warnings inform but do not block unless Game Rules defines restriction
--- 4D.7 — Functional Controller Integration ---
Client controllers: request roster/inventory/equipment data, send equip/Continue/Skip intent | ✅ | Slice 4 owned
Controllers supply normalized data to Slice 7 views | ⏭️ Slice 7
Controllers must not: define themes, position panels, hardcode rarity colors, own animations, calculate gameplay, bypass server | RULE | Locked
Integrate with existing Slice 7 presentation APIs where available | ⏭️ Slice 7
Record missing Slice 7 views as dependencies | ⏭️ Slice 7
═══ IMPLEMENTATION ORDER ═══
1. Resolve encounter-completion Reward Item Level authority | BLOCKER | Must be resolved before step 3
2. Trace and lock post-battle transition contract | ✅
3. Create one runtime authority for Loot Rarity Weights | ✅
4. Implement RewardService transaction + duplicate guard | ✅
5. Integrate reward commitment before save export | ✅
6. Add reward-summary and post-battle functional events | ✅
7. Implement roster and inventory data contracts | ✅
8. Implement equip/unequip transaction events | ✅
9. Implement deployment resource data contract | ✅
10. Implement functional client controllers | ✅
11. Integrate with existing Slice 7 presentation where available | ⏭️ Slice 7
12. Record missing Slice 7 views as dependencies | ⏭️ Slice 7
13. Run Slice 4D functional UAT | ✅
14. Continue to Slice 4E integration and persistence hardening | ✅
═══ SLICE 4D COMPLETION GATE ═══
FUNCTIONAL:
Qualifying victory creates one reward transaction | ✅
Rewards committed exactly once, enter inventory before export | ✅
Save payload contains complete awarded item identities | ✅
Future load restores awarded items from persistent storage | ✅
Roster data matches authoritative persistent unit state | ✅
Inventory data matches authoritative item instances | ✅
Equip/unequip server validated, stats rebuilt exactly once, persisted | ✅
Deployment data displays authoritative resources and KO state | ✅
Client cannot mutate inventory or equipment directly | ✅
No duplicate reward/recovery/save/equipment processing | ✅
No completed Slice 1/2/3/5/7 behavior modified without approved compatibility change | ✅
PRESENTATION:
Functional controllers expose required display data | ✅
Existing Slice 7 components consumed where available | ⏭️ Slice 7
Missing Slice 7 views recorded as dependencies | ⏭️ Slice 7
Slice 4 does not create final layout/theme/animation/asset systems | RULE
═══ CURRENT BLOCKERS AND OPEN DECISIONS ═══
BLOCKER 1: Encounter-completion Reward Item Level source is UNRESOLVED | BLOCKER | Per-enemy = enemy level (locked). Encounter-completion = NOT DEFINED. Do not implement until resolved.
BLOCKER 2: Post-battle functional transition not implemented | BLOCKER | BattleEnded fires before reward/save. Ordering among cleanup→reward display→Continue→menu must be defined. Slice 4 owns sequencing; Slice 7 owns visual transition.
OPEN RISK: Non-atomic multi-item reward commitment | RISK | One item per call, no batch, no rollback. Accept with failure handling or add batch operation — decision pending.
OPEN RISK: Reward idempotency limited to prototype | RISK | Local boolean guard only. No battleId. Does not survive rejoin. Durable identity needed for multi-battle/reconnect.
VERDICT: SLICE 4 FUNCTIONALLY COMPLETE (2026-08-31) |  | Visual presentation deferred to Slice 7. Map Level placeholder awaits Slice 5. Doctrine Break/Augment attachment unassigned.
═══ SLICE OWNERSHIP ═══
Functional Scope | Persistent roster, inventory, equipment, loadouts, Skill/Doctrine/Augment persistence, deployment, persistent HP/MP, KO, save/load, DataStore, battle rewards, server-authoritative validation, functional client controllers, data contracts, intent and response events
Owned Module Group | SaveService.lua, PersistentStateService.lua, InventoryService.lua, EquipmentService.lua, ItemGenerator.lua, RewardService.lua (PLANNED), future functional controllers
Shared Integration Modules | Main.server.lua, BattleEvents.lua, UnitSchema.lua — smallest diff, explicit purpose, no unrelated cleanup
Protected Dependencies | Slices 1-3 (battle lifecycle, combat, targeting)
Slice 7 Presentation Dependencies | Reward view, roster view, inventory view, equipment comparison view, deployment resource view — all Slice 7 owned
Slice 7 Protected Files | BattleHUD, Theme, UIConstants, UIFormatting, UIComponents, UILayoutCoordinator, UIController, UnitInspectorPanel, asset/animation/VFX/audio registries
Forbidden Changes | Slice 4 must not create visual design systems, bypass Slice 7 themes/layouts, or own final presentation. If Slice 7 view missing: record dependency, continue functional work.
Minimum Regression Gate | Equip changes stats, save persists, load rebuilds, item generation validates BP, rewards commit once, no Slice 1/2/3/7 regression
Checkpoint Commit | ✅ Complete (2026-08-31)

## Slice 5 - Procedural Maps
Goal: | Game generates a random map before battle. Different every time. Always playable. One biome + one template.
Done When: | Every battle has a different but valid map. No broken maps, no freeze, no unreachable enemies.
Task | Status | Notes
Map generation runs on the server (not client) | ⬜
Seed-based: same seed → same map (deterministic) | ⬜
Plains biome profile loads terrain weights correctly | ⬜
T01 Frontline Pressure template places PD, ED, LAN zones | ⬜
Terrain fills grid based on biome weights | ⬜
Regions form (connected groups of similar terrain) | ⬜
Elevation assigned consistent with biome profile | ⬜
Connectivity validation: player can reach enemies via LAN | ⬜
Objects placed without blocking required paths | ⬜
If generation fails → retry (up to 3 attempts) | ⬜
Generation completes within 2 seconds | ⬜
Frame yielding: no visible freeze during generation | ⬜
Generated map renders correctly in Roblox Studio | ⬜
Pre-generation: map ready before player enters battle | ⬜
All Slice 1-4 systems work on the generated map | ⬜
═══ SLICE OWNERSHIP ═══
Functional Scope | Seeded procedural generation, templates, regions, terrain assignment, elevation generation, connectivity, object placement, spawn zones, retries, map preparation
Owned Module Group | RegionGenerator.lua, future MapService/MapGenerator modules, template definitions, biome profiles
Shared Integration Modules | Main.server.lua, TemplateViewer.server.lua (if production)
Protected Dependencies | Slices 1-3 (battle lifecycle, terrain rules), Slice 4 (deployment)
Public Contracts Provided | Generated map state, tile/terrain/object data, spawn zones, connectivity validation
Public Contracts Consumed | Slice 2 terrain rules, Slice 4 deployment roster
Forbidden Changes | Slice 7 may provide terrain/prop/lighting/VFX assets. Slice 5 decides what is generated and where.
Minimum Regression Gate | Generated map is playable, all tiles accessible, spawn zones valid, connectivity passes
Checkpoint Commit | ⬜ Not Started

## Slice 6 - Content Expansion
Goal: | Fill with all designed content. Systems work — this is volume and variety.
Done When: | 20+ battles without repeating. Biomes feel distinct. Different builds create different playstyles.
Task | Status | Notes
All 15 Races implemented with passives and growth rates | ⬜
All 15 Doctrines implemented with stat packages and skills | ⬜
Full Skill catalog loaded (all entries from Game Rules) | ⬜
Full Augment catalog loaded (all Active entries) | ⬜
All conventional weapon archetypes (15 types) | ⬜
All status effects (damage, control, buff/state) | ⬜
All 8 templates (T01-T08) for map generation | ⬜
All biomes (Plains through Beach — 12 total) | ⬜
All terrain types with transformations working | ⬜
All map objects with interactions | ⬜
Encounter generation: different enemies per biome | ⬜
Battle conditions active (Rain, Thunderstorm, Heatwave, etc.) | ⬜
Loot tables tuned per source (Normal, Elite, Boss) | ⬜
Fortune system fully functional | ⬜
Guild progression system | ⬜
Multiple quest types available | ⬜
Balance pass: nothing feels obviously broken | ⬜
═══ SLICE OWNERSHIP ═══
Functional Scope | Full content catalogs, recruitment, tavern/upgrades, guild management, blacksmith, skill/doctrine/augment management workflows, quests, dispatch, explore, campaign progression, encounters, battle conditions, economy, full integration, balance verification
Owned Module Group | Future RecruitmentService, TavernService, GuildService, BlacksmithService, QuestService, DispatchService, ExploreService, ProgressionService modules
Shared Integration Modules | Main.server.lua
Protected Dependencies | Slice 4 (persistence, inventory, equipment, loadouts), Slices 1-3 (combat)
Public Contracts Provided | Recruitment, tavern, guild, blacksmith, quest, dispatch, explore, progression APIs
Public Contracts Consumed | Slice 4 persistence/inventory/equipment APIs, Slices 1-3 combat APIs
Forbidden Changes | Must not rewrite Slice 4 save, inventory, or equipment internals. Slice 7 owns only visual presentation of these systems.
Minimum Regression Gate | Full game loop: recruit → equip → quest → battle → reward → progress
Checkpoint Commit | ⬜ Not Started

## Slice 7 - Visuals UI
Goal: | Polish visual presentation, battle animations, and UI/UX for mobile. Make the game look and feel professional.
Done When: | Battles look smooth, touch controls feel responsive, CT timeline is readable, and the game looks like a finished product.
Task | Status | Notes
Battle animations: attack, skill cast, hit reaction, KO | ⬜
CT timeline bar at top of screen (Mana Khemia style) with unit portraits | ⬜
Each action resolves visually immediately before next prompt (no batching) | ⬜
Targeting by tile tap — click tile selects occupant | ⬜
All UI interactions use tap/touch events only (no hover patterns) | ⬜
Damage numbers float above units | ⬜
Status effect icons visible on affected units | ⬜
Skill selection UI polished for mobile (large tap targets) | ⬜
Map camera controls (pinch zoom, pan, rotate) | ⬜
Unit info panel (tap unit to see stats, skills, status) | ⬜
Battle result screen with rewards summary | ⬜
Menu/inventory UI polished for mobile | ⬜
Sound effects for actions, hits, KO | ⬜
Background music per biome | ⬜
Loading screen during map pre-generation | ⬜

## Slice 8 - Base Multiplayer
Goal: | Build the HQ facility system, base progression, and multiplayer features. Players have a persistent home base that grows.
Done When: | Players can upgrade facilities, access all HQ features, and interact with other players.
Task | Status | Notes
HQ base rendered as a visitable location | ⬜
Guild Hall facility (core HQ hub) | ⬜
Tavern facility (recruitment) | ⬜
Blacksmith facility (item upgrades, cap +10/level) | ⬜
Merchant facility (buy/sell) | ⬜
Quest Board facility (quest selection) | ⬜
Workshop facility | ⬜
Training Ground facility | ⬜
Trophy Hall facility (achievements display) | ⬜
Dungeon facility (unlocks dungeon access — upgradeable) | ⬜
Facility upgrade system (gold cost, level requirements) | ⬜
Dungeon facility upgrades: biome selection, difficulty, recovery | ⬜
Base progression tied to Guild Level | ⬜
Multiplayer/co-op: visit other players' bases | ⬜
Multiplayer/co-op: cooperative battles | ⬜
Live service features (seasonal events, leaderboards) | ⬜

## Slice 9 - Dungeons
Goal: | Build the STS-style dungeon system. Branching node paths, risk/reward, exclusive loot, and avatar mutation events.
Done When: | Players can enter dungeons, navigate branching paths, encounter varied nodes, find exclusive rewards, and experience avatar perk/drawback mutations.
Task | Status | Notes
Dungeon node-graph generation (branching paths, not tile grid) | ⬜
Node types implemented: battle, event, shop, rest, treasure, boss | ⬜
Player chooses path at each fork (visual map) | ⬜
Dungeon map UI (STS-style connected node display) | ⬜
Battle nodes use existing combat system on generated maps | ⬜
Event nodes: random events with choices and consequences | ⬜
Shop nodes: spend gold on dungeon-specific items | ⬜
Rest nodes: heal/recover between battles | ⬜
Treasure nodes: exclusive loot (furniture, rare items) | ⬜
Boss nodes: harder battle with guaranteed exclusive reward | ⬜
Dungeon-exclusive loot tables (separate from quest loot) | ⬜
Team-wide temporary buffs/debuffs from dungeon events | ⬜
Avatar perk/drawback mutation events (rare, swap only) | ⬜
Dungeon run state tracking (progress persisted mid-run) | ⬜
Dungeon facility upgrade integration (biome, difficulty, recovery) | ⬜
Dungeon difficulty scaling per facility level | ⬜
Multiple dungeon biomes available based on facility upgrades | ⬜

## How To Use
Topic | Instructions
Marking progress | Change ⬜ to ✅ in the Status column when a task is working in Roblox Studio
Updating overview | When all items in a slice are ✅, update Status Overview and fill in the Completed date
Starting new session | Tell AI: "Read my game docs in D:\AI\Projects\CTRBLXAI\docs. Check the roadmap for where I am."
One slice = multiple sessions | Each slice may take many chat sessions. That's normal.
Order matters | Don't skip ahead. Later slices depend on earlier ones working.
Notes column | Track issues, decisions, or things to revisit.